## Issue-Log
ISSUE MANAGEMENT LOG
Project Name: |  |  | Internet Banking System
Project Manager Name: |  |  | Osama Sayed
Project Ref:
ID | Status | Priority | Issue Description | Owner | Estimated Resolution Date | Escalation Needed (Y/N)? | Impact | Actions | Date Identified | Logged By | Actual Resolution/Completion Date | Final Resolution & Follow-on actions
001 | Closed | Critical | Issues raised by board members about the configuration management tool and bush related to the deadline of the first release and milestone. | PM | 15/4/2022 | Yes | Potential project cancellation or significant delay. | Meet with board members to try to sovle the problem by asking them if anyone has a knowlage and can use the CM tool | 15/4/2022 | Osama Sayed | 15/4/2022 | One of the team members could used the tool and uploud the work berfor the deadline.
|  |  | This template was provided by | https://www.stakeholdermap.com/
Note on A7: A unique ID number
Note on B7: Status: - Open: The issue is currently open but has not yet been addressed. - Work In Progress: The issue is being actively worked to develop a resolution. - Closed: The issue is no longer considered an active project threat and can be closed with or without resolution.
Note on C7: Critical, High, Medium, Low. Critical: Issue will stop project progress. High: Issue will likely impact budget, schedule or scope. Medium: Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope. Low: Issue is low impact and/or low effort to resolve.
Note on D7: Give a brief description of the issue.
Note on E7: The individual most responsible for working towards resolving the issue.
Note on F7: Estimated or target date for completion of actions.
Note on G7: “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on H7: Describe the impact of the issue. This may be in terms of the project constraints of time, cost and scope. See http://www.stakeholdermap.com/project-management/project-triangle.html
Note on I7: Actions to mitigate the issue, avoid the issue or resolve the issue.
Note on J7: The date that the issue was identified.
Note on L7: Actual completion date.
Note on M7: Document the final outcome. Is the issue resolved and if so how? Are there any follow-on actions? Are there any follow-on risks?

## severity-levels
Issue severity | Description
Critical | Issue will stop project progress.
High | Issue will likely impact budget, schedule or scope.
Medium | Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope.
Low | Issue is low impact and/or low effort to resolve.
| This template was provided by | https://www.stakeholdermap.com/

## RESOURCES
Project Management resources
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
20 Common Project Risks
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel

## CUSTOMIZE
How to change or remove the cell colours in the Priority and 'Escalation needed?' column.
Conditional formatting is used to set the cell fill colour.
To change the fill colour. Click on Home > Conditional Formatting > Manage Rules…