## PMP
Review No. | Raised By | Issue Date | Issue | Status | Approved By | Closed date
PMP_1 | Mostafa | 13/4/2022 | Change Control Management is missing some details | Open | PM
PMP_2 | Aya | 13/4/2023 | Schedule and dependencies is missing | Closed | PM | 14/4/2023
PMP_3 | Mariam | 14/4/2025 | Some Description in appendix doesn’t written | Open | PM

## Options (hidden)
Open
Close

## SRS
Review No. | Raised By | Issue Date | Issue | Status | Approved By | Closed date
RV_01 | Mostafa | 13/4/2022 | Forgot clear the highlight of section 2.6, Appendix B and C | Close | PM | 14/4/2022
RV_02 | Osama Sayed | 13/4/2023 | section 3.2.3 in Error conditions for login & logout feature requirements in last section the sentence is "password are blank" should be "Password is". | Close | PM | 14/4/2023
RV_03 | Aya | 13/4/2024 | section 3.5.3 and section 3.8.3 sentence is "Error conditions for add" should be "for adding". | Close | PM | 14/4/2024
RV_04 | Osama Sayed | 13/4/2023 | section 3.6.3 sentence is "Error conditions for edit" should be "Error conditions for editing". | Close | PM | 14/4/2025
RV_05 | Osama Sayed | 13/4/2024 | Section 4.4 in Accuracy word "programme" have to "program" | Close | PM | 14/4/2026
Close
Close

## Progress_Chart
PMP | Open | 0 | SRS | Open | 2
| Closed | 5 |  | Closed | 1
| Total | 5 |  | Total | 3