## WBS Tree Diagram - BLANK
WORK BREAKDOWN STRUCTURE TREE DIAGRAM TEMPLATE
PROJECT TITLE | Internet Banking System | COMPANY NAME | ITI
PROJECT MANAGER | Osama | DATE | 2022-04-12
Internet Banking System
1.0 Launch project
1.1 Complete Stakeholder Research
1.3 initial Implementation Plan
1.1.1 Stakeholder Interviews
1.1.2 Stakeholder Analysis
1.3.1.1 Project Charter
1.3.1.2 Project Scope definition
1.3.1.3 Initial project plan
1.3.1.4 Initial communication strategyr
1.3.1.5 Initial Risk Analysis
1.3.1.6 Issue Mamangment
1.3.1.7 Intial chanage Managment plan
1.3.1.8 Schedule Managment Time
1.3.1.9 Intial Quality Managment plan
1.3.1 Project Management documentation
1.3.2 Track project
1.3.3 perform Quality Activites
1.3.3.1 prepare QA plan
1.3.3.2 Conduct Reviews
1.3.3.3 Conduct Audits
1.3.2.1 Prepare status reports
1.3.2.2 Collect/analyze project metrics
1.3.4 perform Configuration Management
1.3.4.1 Scope & SCM activities
1.3.4.2 SCM organizational role
1.3.4.3
Identification & Description
1.3.4.4 Work products & Documentation
1.3.4.5 Configuration Control
1.3.4.6 Version Control
1.3.4.7 Reviews and Audits
1.3.4.8 Problem Reporting and Corrective Actions
3.0 Development
3.2 Front End
3.2.1 Login /Registration
3.2.2 Admin UI
3.2.3 transefer money 3.2.5 transaction History
3.1.1 Prepare Database
3.1.2 login /Registration
3.1.3 Admin page
3.1.4 transefer money
3.1.5 Transaction History
3.1 Back end
4.0 Testing
4.1 Testing sterategy
4.2 test plan
4.3 Unit Test
4.4 Integrtion Test
4.5 System Test
4.6 Acceptnce Test
1.2 Requirement Gathering
1.2.1 User Requirement
1.2.2 Technical Specification
2.0 Design
2.1 High level Design
2.2 low level Design