## Changes
Project Desctiption | The internet banking system is relevant everywhere where banking exists. All banks will favor an online banking system over the traditional banking systems as it has more features and provides faster Transfer methods..
ID | Current Status | Change Description | Impact Summary | Solution | Date Identified | Entered By | Actual Resolution Date
Change_01 | Closed | Replacing the Project manager with another project manager from another team | managerial tasks are left unassigned the new project manager has very little knowledge about the project | all the managerial tasks are assigned to the new Project manager the team memebers help in the handover to the project manager | 2022-07-05 | Hassan | 2022-08-05
Change_02 | Closed | Replacing one of the team members with another member | Little knowledge about the project Some Tasks are left unassigned | The team should help the new member with a walkthrough the project the Project manager should reassign the tasks based on the new set of skills in the team | 2022-07-05 | Hassan | 2022-08-05
Change_03 | Closed | Add new Requirement that the user should be able to change between 2 currencies in money transfer [ USD and EPG] | This new requirement is missing from SRS Document , the scope statement , also front-end and back-end and the RTM. | The frontend and backend code should be modified and the new requirement should be implemented. The relevant documents should be reviewed and the new requirement should be added if needed. The new requirement should be added in the SRS. The RTM should be updated. | 14/5/2022 | Esraa
Change_04 | Closed | Add new Requirement that the USD should have a default value | The new requirement is missing from the backend code , the RTM and all documents including SRS. | The backend code should be modified and the new requirement should be implemented. The relevant documents should be reviewed and the new requirement should be added if needed. The new requirement should be added in the SRS. The RTM should be updated. | 14/5/2022 | Esraa
Change_05 | Closed | Add new requirement that the USD should be equal to 15 EGP. | The new requirement is missing from the backend code , the RTM and all documents including SRS. | The backend code should be modified and the new requirement should be implemented. The relevant documents should be reviewed and the new requirement should be added if needed. The new requirement should be added in the SRS. The RTM should be updated. | 14/5/2022 | Esraa
Change_06 | Closed | Add restrictions for strong password should be applied [ shall contain Upper and lower cases charters and one special character and at least 8 numbers | This new requirement is missing from SRS Document , front-end and the RTM. | The frontend code should be modified and the new requirement should be implemented. The new requirement should be updated in SRS and RTM. | 14/5/2022 | Esraa
Note on A2: ====== ID#AAAAZG8zDMM eze3 (2022-05-16 16:50:59) • ID: A unique ID number used to identify the change request in the change management log.
Note on B2: ====== ID#AAAAZG8zDME eze3 (2022-05-16 16:50:59) • Current Status: This column should be populated with the change request's current status. o Open: The change request is currently open but has not yet been addressed. o Work In Progress: The change request is being actively worked to develop a resolution. o Closed: The change request is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The change request resolution is not yet resolved and it is past the expected resolution date. o On Hold: The change request has been put on hold. o Combined: Two change request found to be similar have been combined.
Note on C2: ====== ID#AAAAZG8zDMY eze3 (2022-05-16 16:50:59) • Change Request Description: This column should be populated with a description of the change request.
Note on D2: ====== ID#AAAAZG8zDMc eze3 (2022-05-16 16:50:59) • Impact Summary: This column should be populated with a description of the impact of the change request. The impact may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The impact description should also include a reference to any milestones impacted.
Note on E2: ====== ID#AAAAZG8zDMU eze3 (2022-05-16 16:50:59) • Action Steps: This column should be populated with the proposed steps to address the change request. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
Note on F2: ====== ID#AAAAZG8zDMg eze3 (2022-05-16 16:50:59) • Date Identified: This column should be populated with the date that the change request was identified.
Note on G2: ====== ID#AAAAZG8zDMI eze3 (2022-05-16 16:50:59) • Entered By: This column should be populated with the name of the individual who first identified the change request.
Note on H2: ====== ID#AAAAZG8zDMQ eze3 (2022-05-16 16:50:59) • Actual Resolution Date: This column should be populated with the date that the change request was actually resolved.

## draft changes
Document name | change
SRS | 3.3 transfer money USD currency to the supported Currencies
SRS | 3.3.3.4 Transfer money currency requirements -Added another sub requirement [BS – REQ – TM12]
Scope Statement | -Added functionallity to in scope at scope description
Scope Statement | -change PM from osama to saad
Project Charter | -Change PM from Osama to Saad -Change Developer and Tester Role from Mostafa to Yara
RTM | -Added the new sub requirmenet [BS – REQ – TM12] to Software Requirement