## PMP
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
PMP_01 | Mostafa | PM | 13/4/2022 | Change Control Management is missing some details | Close | PM
PMP_02 | Aya | PM | 2022-04-13 | Schedule and dependencies is missing | Close | PM | 2022-04-14
PMP_03 | Mariam | PM | 2022-04-14 | Some Description in appendix doesn’t written | Close | PM

## Testcases
Client Registration Module
Review No. | Raised By | Assigned to | Issue Date | Issue | Related Testcase ID or Module name | Status | Approved By | Closed date
TC_CR_01 | Yara | Nada | 25-5-2022 | Testcase Description not clear and there is only one register button. | TC_BS_Client_REG_03 | closed | Yara | 2022-05-26
TC_CR_02 | Yara | Nada | 25-5-2022 | Testcase Expected Result should be also be changed after TC_CR_01 is corrected. | TC_BS_Client_REG_03 | closed | Yara | 2022-05-26
TC_CR_03 | Yara | Nada | 25-5-2022 | Can not understand the meaning of Testcase Description. | TC_BS_Client_REG_05 | closed | Yara | 2022-05-26
TC_CR_04 | Yara | Nada | 25-5-2022 | Testcase Description needs to be more detailed and clear. | TC_BS_Client_REG_14 | closed | Yara | 2022-05-26
TC_CR_05 | Yara | Nada | 25-5-2022 | This Testcase should be splited to two testcases. | TC_BS_Client_REG_18 | closed | Yara | 2022-05-26
TC_CR_06 | Yara | Nada | 25-5-2022 | Requirement with ID [BS – REQ – CR11] has no testcase | - | closed | Yara | 2022-05-26
TC_CR_07 | Yara | Nada | 25-5-2022 | This Testcase should be splited to two testcases. | TC_BS_Client_REG_24 | closed | Yara | 2022-05-26
Client Login Module
Review No. | Raised By | Assigned to | Issue Date | Issue | Related Testcase ID or Module name | Status | Approved By | Closed date
TC_CL_01 | Yara | Sara | 25-5-2022 | Testcase Description should start with verb to describe the reason for this test case like (validate). | Client Login Module | closed | Yara | 2022-05-26
TC_CL_02 | Yara | Sara | 25-5-2022 | Testcase Steps should be more detailed. | Client Login Module | closed | Yara | 2022-05-26
TC_CL_03 | Yara | Sara | 25-5-2022 | Testcase Expected Result should contain error message written clearly. | Client Login Module | closed | Yara | 2022-05-26
Admin Login Module
Review No. | Raised By | Assigned to | Issue Date | Issue | Related Testcase ID or Module name | Status | Approved By | Closed date
TC_AL_01 | Yara | Sara | 25-5-2022 | Testcase Description should start with verb to describe the reason for this test case like (validate). | Admin Login Module | closed | Yara | 2022-05-26
TC_AL_02 | Yara | Sara | 25-5-2022 | Testcase Steps should be more detailed. | Admin Login Module | closed | Yara | 2022-05-26
TC_AL_03 | Yara | Sara | 25-5-2022 | Testcase Expected Result should contain error message written clearly. | Admin Login Module | closed | Yara | 2022-05-26
Add Client Module
Review No. | Raised By | Assigned to | Issue Date | Issue | Related Testcase ID or Module name | Status | Approved By | Closed date
TC_AC_01 | Aya | Saad | 25-5-2022 | This testcase's preconditions doesn't include Client's username used in test data doesn't exsit on the system's database | TC_BS_Add_Client_01 | Closed | Aya | 2022-05-26
Edit Client Module
Review No. | Raised By | Assigned to | Issue Date | Issue | Related Testcase ID or Module name | Status | Approved By | Closed date
TC_19 | Yara | Aya | 26-5-2022 | The data inserted instead of edited so only the edited fields should be mentiond not all the input fields | "TC_BS_Edit_Client_05" to "TC_BS_Edit_Client_19" | Closed | Yara | 2022-05-26
TC_21 | Yara | Aya | 26-5-2022 | SRS requirement related to this testcase is not correct | TC_BS_Edit_Client_06 | Closed | Yara | 2022-05-26
Delete Client Module
Review No. | Raised By | Assigned to | Issue Date | Issue | Related Testcase ID or Module name | Status | Approved By | Closed date
TC_DC_01 | Mariam | Yara | 25-5-2022 | This testcase's preconditions doesn't include that the admin is successfully logged in | TC_BS_Delete_Client_01 | Closed | Mariam | 2022-05-26
Add Account Module
Review No. | Raised By | Assigned to | Issue Date | Issue | Related Testcase ID or Module name | Status | Approved By | Closed date
TC_AA_01 | SaRa | Nada | 26-5-2022 | The test case should contain more details as a Admin must login successfully to has the ability to add an account | Admin Add Account | Closed | SaRa | 2022-05-26
TC_AA_02 | SaRa | Nada | 26-5-2022 | The cells in the sheet should start with upper case | Admin Add Account | Closed | SaRa | 2022-05-26
TC_AA_03 | SaRa | Nada | 26-5-2022 | Check this requirement in the [BS – REQ – AA8] in SRS , to write the expected result correctly | BS_AddAcc_04 | Closed | SaRa | 2022-05-26
TC_AA_04 | SaRa | Nada | 26-5-2022 | Write the field name correctly without an abbreviation | Admin Add Account | Closed | SaRa | 2022-05-26

## ERD
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
ERD_01 | Aya | PM | 2022-05-09 | Client Name should be changed to User Name | Close | Aya | 2022-05-10
ERD_02 | Aya | PM | 2022-05-09 | Admin Name should be Changed to User Name | Close | Aya | 2022-05-10

## Options (hidden)
Open
Close
Work in progress

## SRS
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
RV_01 | Mostafa | Sara | 13/4/2022 | Forgot clear the highlight of section 2.6, Appendix B and C | Close | PM | 14/4/2022
RV_02 | Osama Sayed | Sara | 13/4/2023 | section 3.2.3 in Error conditions for login & logout feature requirements in last section the sentence is "password are blank" should be "Password is". | Close | PM | 14/4/2023
RV_03 | Aya | Sara | 13/4/2024 | section 3.5.3 and section 3.8.3 sentence is "Error conditions for add" should be "for adding". | Close | PM | 14/4/2024
RV_04 | Osama Sayed | Sara | 13/4/2023 | section 3.6.3 sentence is "Error conditions for edit" should be "Error conditions for editing". | Close | PM | 14/4/2025
RV_05 | Osama Sayed | Sara | 13/4/2024 | Section 4.4 in Accuracy word "programme" have to "program" | Close | PM | 14/4/2026
RV_06 | Saad | -- | 26/5/2022 | ---

## SDD
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
SDD_01 | Mariam | Saad | 2022-05-17 | "Transaction methods" in the "Summary of the project" section should be changed to Transfer to be consistent with the rest of the documents. | Closed | Mariam | 2022-05-17
SDD_02 | Mariam | Saad | 2022-05-17 | In section 3.8 transfer money , convertToEGP function should be added to called functions for sourceAccountHasSufficentBalance function. | Closed | Mariam | 2022-05-17

## Back End
Review No. | Raised By | Issue Date | Assigned to | Issue | Status | Approved By | Closed date
CODE_01 | Mariam | 19-5-2022 | Saad | Wrong Redirect from Client Registration to client profile page "ClientRegistraion Page" | Closed | Mariam | 19-5-2022
CODE_02 | Mariam | 19-5-2022 | Saad | A server error occurs when a new client is added with the same account number as another existing client in the ClientRegistration Page. | Closed | Mariam | 19-5-2022
CODE_03 | Aya | 19-5-2022 | Mariam | A server error occurs when a new client is added with the same account number as another existing client in the AddClient Page. | Closed | Aya | 19-5-2022
CODE_04 | Aya | 19-5-2022 | Mariam | The logged in admin is not recorded in the database in the AddClient Page. | Closed | Aya | 19-5-2022

## Front End
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
FE_01 | Saad | Mariam & Yara | 2022-05-10 | All HTML5 tags should be converted to asp tags | Closed | Saad | 2022-05-10
FE_02 | Yara | Mariam | 2022-05-10 | Register button size in the wireframe design doesn't match with the wireframe design with ID (Client Registration_WF_02) | Closed | Yara | 2022-05-11
FE_03 | Yara | Mariam | 2022-05-10 | Add client button size in the wireframe design doesn't match with the wireframe design with ID (Add Client_WF_08) | Closed | Yara | 2022-12-05
FE_04 | Yara | Mariam | 2022-05-10 | Edit button size in the wireframe design doesn't match with the wireframe design with ID (Edit Client Step1_WF_09) | Closed | Yara | 2022-12-05
FE_05 | Yara | Mariam | 2022-05-10 | Edit button size in the wireframe design doesn't match with the wireframe design with ID (Edit Client Step2_WF_10) | Closed | Yara | 2022-12-05
FE_06 | Mariam | Yara | 2022-05-11 | In case of scrolling right , header and footer don't match the wireframe design with ID(Home_WF_01) | Closed | Mariam | 2022-12-05
FE_07 | Mariam | Yara | 2022-05-11 | Background image is missing in the front end but it exists in wirefame with ID(Transfer Money_WF_05) | Closed | Mariam | 2022-12-05
FE_08 | Mariam | Yara | 2022-05-11 | Amount field doesn't accept float numbers because of a pattern used in the amount field front end | Closed | Mariam | 2022-05-11
FE_09 | Mariam | Yara | 2022-05-11 | There is a frame called frame html which is an unreadable name | Closed | Mariam | 2022-12-05
FE_10 | Mariam | Yara | 2022-05-11 | The links in the left part of the design are not centered as they are in the wireframe (Admin Dashboard_WF_07) | Closed | Mariam | 2022-12-05
FE_11 | Mariam | Yara | 2022-05-10 | Delete button size in the wireframe design doesn't match with the wireframe design with ID (Delete Client_WF_11) | Closed | Mariam | 2022-12-05

## Wireframe
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
WF_01 | Yara | Mariam | 2022-05-10 | TextBox "Account Number" at Register Page does not match TextBox "Bank Account Number" at wireframe with ID(Client Register_WF_02) | Closed | Yara | 2022-05-11

## Database
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date

## Progress_Chart
PMP | Open | 0 | SRS | Open | 0
| Work in progress | 2 |  | Work in progress | 0
| Closed | 1 |  | Closed | 5
| Total | 3 |  | Total | 5