## RACI Matrix Template
RACI Matrix Template
Project Tasks | osama | Mostafa | Aya | sara | Nada | Mariam | Customer
Initiation Phase
SIQ | I | C | C | R | C | C | A
Planning Phase
PMP | R/A | C | C
Documentation
SRS | A/I | C | C | C |  | R
Control Phase
Configratiom management | A/I |  |  |  | R
Design
High Level design | I | A | C |  |  | R
Low Level design | I | A | C | R
Development
Back End | I | A | R | C |  | C
Front End | I | A | R | C |  | C
Testing
Unite test | I | R/A | C | C |  | C
Integration test | I | R/A | C | C |  | C
System test | I | P/A | C | C |  | C
Acceptance test | I | R/A | C | C |  | C
Responsible
Accountable
Consulted
Informed