## Changes
Project Desctiption | The internet banking system is relevant everywhere where banking exists. All banks will favor an online banking system over the traditional banking systems as it has more features and provides faster Transfer methods..
ID | Current Status | Change Description | Impact Summary | Solution | Date Identified | Entered By | Actual Resolution Date
Change_01 | Closed | Replacing the Project manager with another project manager from another team | managerial tasks are left unassigned the new project manager has very little knowledge about the project | all the managerial tasks are assigned to the new Project manager the team memebers help in the handover to the project manager | 2022-07-05 | Hassan | 2022-08-05
Change_02 | Closed | Replacing one of the team members with another member | Little knowledge about the project Some Tasks are left unassigned | The team should help the new member with a walkthrough the project the Project manager should reassign the tasks based on the new set of skills in the team | 2022-07-05 | Hassan | 2022-08-05
Change_03 | Open | Add new Requirement that the user should be able to change between 2 currencies in money transfer [ USD and EPG] | This new requirement is missing from SRS Document , the scope statement , also front-end and back-end and the RTM. | The frontend and backend code should be modified and the new requirement should be implemented. The relevant documents should be reviewed and the new requirement should be added if needed. The new requirement should be added in the SRS. The RTM should be updated. | 14/5/2022 | Esraa
Change_04 | Open | Add new Requirement that the USD should have a default value | The new requirement is missing from the backend code , the RTM and all documents including SRS. | The backend code should be modified and the new requirement should be implemented. The relevant documents should be reviewed and the new requirement should be added if needed. The new requirement should be added in the SRS. The RTM should be updated. | 14/5/2022 | Esraa
Change_05 | Open | Add new requirement that the USD should be equal to 15 EGP. | The new requirement is missing from the backend code , the RTM and all documents including SRS. | The backend code should be modified and the new requirement should be implemented. The relevant documents should be reviewed and the new requirement should be added if needed. The new requirement should be added in the SRS. The RTM should be updated. | 14/5/2022 | Esraa
Change_06 | Open | Add restrictions for strong password should be applied [ shall contain Upper and lower cases charters and one special character and at least 8 numbers | This new requirement is missing from SRS Document , front-end and the RTM. | The frontend code should be modified and the new requirement should be implemented. The new requirement should be updated in SRS and RTM. | 14/5/2022 | Esraa

## draft changes
Document name | change
SRS | 3.3 transfer money USD currency to the supported Currencies
SRS | 3.3.3.4 Transfer money currency requirements -Added another sub requirement [BS – REQ – TM12]
Scope Statement | -Added functionallity to in scope at scope description
Scope Statement | -change PM from osama to saad
Project Charter | -Change PM from Osama to Saad -Change Developer and Tester Role from Mostafa to Yara
RTM | -Added the new sub requirmenet [BS – REQ – TM12] to Software Requirement