## Audit
Project Name: | Internet Banking System
Team Number: | A
Comment ID | Commented By | Document Ref. | Comment | Comment Date | Assigned to | Status | Close Date
Comment_01 | Esraa | RTM | Tasks should be scheduled including Review and Tracability | 2022-07-05 | Saad | Open
Comment_02 | Esraa | Design Document | Design Document | 2022-07-05 | Saad | Open
Comment_03 | Esraa | Review Sheet | Adding review sheet to GitHub | 2022-07-05 | Mariam | Open
Comment_04 | Esraa | SRS | Naming Consistency in SRS | 2022-07-05 | Mariam | Open
Comment_05 | Esraa | CIL | CI List | 2022-07-05 | Nada H. | Open
Comment_06 | Esraa | Audit Sheet | Adding comments to comments file in audit | 2022-07-05 | Yara | Open
Comment_07 | Esraa | Design Folder | Restructure HLD and LLD as requested | 2022-07-05 | Yara | Close
Comment_08 | Esraa | WBS | Cover page for WBS | 2022-07-05 | Aya S. | Open
Comment_09 | Esraa | ERD | Date should be included in ERD | 2022-07-05 | Aya S. | Close
Comment_10 | Esraa | SRS,PMP,Designs | Naming consistency between documents and Sequence diagrams | 2022-07-05 | Sara H. | Open