## PMP
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
PMP_1 | Mostafa | PM | 13/4/2022 | Change Control Management is missing some details | Work in progress | PM
PMP_2 | Aya | PM | 2022-04-13 | Schedule and dependencies is missing | Close | PM | 2022-04-14
PMP_3 | Mariam | PM | 2022-04-14 | Some Description in appendix doesn’t written | Work in progress | PM

## ERD
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
ERD_1 | Aya | PM | 2022-05-09 | Client Name should be changed to User Name | Close | Aya | 2022-05-10
ERD_2 | Aya | PM | 2022-05-09 | Admin Name should be Changed to User Name | Close | Aya | 2022-05-10

## Options (hidden)
Open
Close
Work in progress

## SRS
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
RV_01 | Mostafa | Sara | 13/4/2022 | Forgot clear the highlight of section 2.6, Appendix B and C | Close | PM | 14/4/2022
RV_02 | Osama Sayed | Sara | 13/4/2023 | section 3.2.3 in Error conditions for login & logout feature requirements in last section the sentence is "password are blank" should be "Password is". | Close | PM | 14/4/2023
RV_03 | Aya | Sara | 13/4/2024 | section 3.5.3 and section 3.8.3 sentence is "Error conditions for add" should be "for adding". | Close | PM | 14/4/2024
RV_04 | Osama Sayed | Sara | 13/4/2023 | section 3.6.3 sentence is "Error conditions for edit" should be "Error conditions for editing". | Close | PM | 14/4/2025
RV_05 | Osama Sayed | Sara | 13/4/2024 | Section 4.4 in Accuracy word "programme" have to "program" | Close | PM | 14/4/2026

## SDD
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
SDD_01 | Mariam | Saad | 2022-05-17 | "Transaction methods" in the "Summary of the project" section should be changed to Transfer to be consistent with the rest of the documents. | Closed | Mariam | 2022-05-17
SDD_02 | Mariam | Saad | 2022-05-17 | In section 3.8 transfer money , convertToEGP function should be added to called functions for sourceAccountHasSufficentBalance function. | Closed | Mariam | 2022-05-17

## Back End
Review No. | Raised By | Issue Date | Assigned to | Issue | Status | Approved By | Closed date
CODE_01 | Mariam | 19-5-2022 | Saad | Wrong Redirect from Client Registration to client profile page "ClientRegistraion Page" | Closed | Mariam | 19-5-2022
CODE_02 | Mariam | 19-5-2022 | Saad | A server error occurs when a new client is added with the same account number as another existing client in the ClientRegistration Page. | Closed | Mariam | 19-5-2022
CODE_03 | Aya | 19-5-2022 | Mariam | A server error occurs when a new client is added with the same account number as another existing client in the AddClient Page. | Closed | Aya | 19-5-2022
CODE_04 | Aya | 19-5-2022 | Mariam | The logged in admin is not recorded in the database in the AddClient Page. | Closed | Aya | 19-5-2022

## Front End
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
FE_01 | Saad | Mariam & Yara | 2022-05-10 | All HTML5 tags should be converted to asp tags | Closed | Saad | 2022-05-10
FE_02 | Yara | Mariam | 2022-05-10 | Register button size in the wireframe design doesn't match with the wireframe design with ID (Client Registration_WF_02) | Closed | Yara | 2022-05-11
FE_03 | Yara | Mariam | 2022-05-10 | Add client button size in the wireframe design doesn't match with the wireframe design with ID (Add Client_WF_08) | Closed | Yara | 2022-12-05
FE_04 | Yara | Mariam | 2022-05-10 | Edit button size in the wireframe design doesn't match with the wireframe design with ID (Edit Client Step1_WF_09) | Closed | Yara | 2022-12-05
FE_05 | Yara | Mariam | 2022-05-10 | Edit button size in the wireframe design doesn't match with the wireframe design with ID (Edit Client Step2_WF_10) | Closed | Yara | 2022-12-05
FE_06 | Mariam | Yara | 2022-05-11 | In case of scrolling right , header and footer don't match the wireframe design with ID(Home_WF_01) | Closed | Yara | 2022-12-05
FE_07 | Mariam | Yara | 2022-05-11 | Background image is missing in the front end but it exists in wirefame with ID(Transfer Money_WF_05) | Closed | Mariam | 2022-12-05
FE_08 | Mariam | Yara | 2022-05-11 | Amount field doesn't accept float numbers because of a pattern used in the amount field front end | Closed | Mariam | 2022-05-11
FE_09 | Mariam | Yara | 2022-05-11 | There is a frame called frame html which is an unreadable name | Closed | Mariam | 2022-12-05
FE_10 | Mariam | Yara | 2022-05-11 | The links in the left part of the design are not centered as they are in the wireframe (Admin Dashboard_WF_07) | Closed | Mariam | 2022-12-05
FE_11 | Mariam | Yara | 2022-05-10 | Delete button size in the wireframe design doesn't match with the wireframe design with ID (Delete Client_WF_11) | Closed | Mariam | 2022-12-05

## Wireframe
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date
WF_01 | Yara | Mariam | 2022-05-10 | TextBox "Account Number" at Register Page does not match TextBox "Bank Account Number" at wireframe with ID(Client Register_WF_02) | Closed | Yara | 2022-05-11

## Database
Review No. | Raised By | Assigned to | Issue Date | Issue | Status | Approved By | Closed date

## Progress_Chart
PMP | Open | 0 | SRS | Open | 0
| Work in progress | 2 |  | Work in progress | 0
| Closed | 1 |  | Closed | 5
| Total | 3 |  | Total | 5